## Summary-GroupIterationProgress
This report consists of multiple sheets: 1. the group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 2. the project ontribution sheet to be filled by everyone at the end of the semester, 3. the AI Usage Log to be filled by everyone whenever using AI tools 4. the weekly report sheet, one per teamember member, to be filled in each week.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/18/2026–09/26/2026 | Held two Discord voice meetings: assigned six team roles and completed GitHub Lab 1 introductions on 09/18; discussed the AI Movie Recommendation Chat Bot proposal and prepared the first SPPP draft by 09/26. Defined scope, requirements, a three-iteration plan, risks, and collaboration practices. | Potential integration and external API risks identified in the SPPP; no confirmed implementation issues recorded for Iteration 0. | Limited development time and coordination among six members were identified as risks. No specific coordination incident was recorded. | For Iteration 1, break the core requirements into user stories, confirm owners and dates, set up the development workflow, and begin the basic chat interface and movie recommendation functions. | 0 | 0 | 0 | 0 | 0 | 16 | 2 for each | 4 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | SPPP proposes tracking completed user stories, test pass rate, defects, and recommendation relevance. No measured Iteration 0 values were supplied.
1
2
3

## AIUsageLog
This sheet records all AI usage by your team members
Who | When | Tools | Tasks & Artifact | Final Use (Accepted / Modified / Rejected) | Evaluation/Modification | Link /Appendix/ Prompt history + output summary

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6