## Slide 1
AI Movie Recommendation
Chat Bot
CS673 Software Engineering
Team 1
Iteration 0: Project Proposal and Planning
Notes: Hello everyone. We are Team 1, and our project is an AI movie recommendation chatbot. It helps users discover movies through natural language. A user can describe a genre, mood, or preferred runtime, and receive suitable recommendations. Our target users are people who want a faster, easier way to choose a movie. This iteration zero presentation covers our proposed scope, technical approach, development plan, and main risks. Our first priority is a working chatbot in a web interface. The features and technologies we discuss are plans, rather than completed implementation.

## Slide 2
Core features and scope
Essential
Natural language requests, a movie list, and visible recognized preferences
Desirable
Movie details, follow-up refinement, and a personal watchlist
Optional
Multiple languages, playback links, and platform information
02
Notes: Our essential features are natural language input, a recommended movie list, and a display of the preferences the chatbot recognized. For example, a user might ask for a recent comedy, and the interface would show the detected genre and year preference. Desirable features include movie details, follow-up refinement, and a personal watchlist. If time allows, we may add multilingual support and information about where to watch each movie. We will prioritize the core recommendation experience. Additional features will follow only when that basic workflow works reliably and the team has enough time.

## Slide 3
Proposed technology
Web interface
HTML/CSS/JavaScript or React for chat and movie results
Backend
Python or Java to process requests and coordinate services
External services
Movie database API for information and AI API for request interpretation
03
Notes: The proposed system has a frontend, a backend, and external services. The frontend could use HTML, CSS, and JavaScript, or React. The backend could use Python or Java. A movie database API would provide movie information, while an AI API would help interpret user requests. We still need to confirm the final stack. The product must be a presentable web application, even if we use notebooks for early experiments. Our main technical task is to connect preference recognition with movie retrieval, then return clear, useful recommendations through the chat interface.

## Slide 4
Three-iteration development plan
Iteration 1 25–35 person-hours
Environment setup, basic UI, movie API, and basic chatbot
Iteration 2 30–40 person-hours
Database, frontend/backend integration, filters, and recommendation logic
Iteration 3 20–25 person-hours
Refinement, history/feedback, security review, testing, and deployment
04
Notes: We plan three development iterations. Iteration one covers environment setup, a basic interface, movie API integration, and the basic chatbot. Its estimate is twenty-five to thirty-five person-hours. Iteration two adds movie information, filters, a database, and frontend and backend integration. Its estimate is thirty to forty person-hours. Iteration three focuses on refinement, history and feedback, testing, security review, deployment, and documentation. Its estimate is twenty to twenty-five person-hours. The estimated total is seventy-five to one hundred person-hours. These are team effort estimates. We still need to assign individual tasks and confirm the schedule.

## Slide 5
Example user interaction
User request
“Recommend a comedy released after 2020, under 2 hours.”
Recognized preferences:
Comedy
After 2020
Under 120 minutes
Proposed chatbot response
A list of matching movies with brief descriptions and ratings
Follow-up request:
“Show me something similar.”
05
Notes: This example shows how we expect the chatbot to work. A user asks for a comedy released after 2020 and shorter than two hours. The system recognizes three preferences: the comedy genre, a release year after 2020, and a runtime under 120 minutes. It then returns matching movies with brief descriptions and ratings. Showing the recognized preferences lets the user check whether the chatbot understood the request. The user could then ask for something similar, using the follow-up refinement feature. This is a proposed interaction example. It illustrates our intended experience rather than a demonstration of a completed system.

## Slide 6
Quality, security, and teamwork
Product requirements
Response target: within 3 seconds
Responsive desktop and mobile UI
Server-side API keys and input sanitization
Team workflow
Feature branches and peer PR review
Unit and integration tests
GitHub Actions checks and Issues for defects
06
Notes: We aim to return recommendations within three seconds under normal network conditions. The interface should work on desktop and mobile browsers. API keys must remain on the server, and the proposal calls for input sanitization to address security risks. Our six team roles cover leadership, requirements, implementation, configuration, quality assurance, and security. Developers will use feature branches and ask another member to review each pull request. They will test their own components, while the QA leader focuses on integration. GitHub Actions will support automated checks, and GitHub Issues will track defects.
Source: Copy of CS673_SPPP.docx, project proposal and planning, version 0, 09/26/2026.

## Slide 7
Risks and next steps
Limited development time
Prioritize the essential chatbot and divide tasks clearly
Integration problems
Test components throughout development and review merged work
External API problems
Evaluate simpler local alternatives if a service is unavailable
.
07
Notes: Our main risks are limited time, integration problems, and dependence on external APIs. We will manage time by building essential features first and dividing tasks clearly. Frequent testing and peer review will help us catch integration problems early. If an external service is unavailable or too difficult to integrate, we may use a simpler local solution to preserve the core functionality. Our next steps are to confirm the technology stack, assign iteration one tasks, and build the first working recommendation flow. That gives us a baseline for later improvements. Thank you, and we welcome questions.